## MIDP
Z
Program /Project Manager Name: | SEDRA 345 ( VERTICALS )
BIM Manager: | Abrar Ahmed
Project Title: | SEDRA 3/4/5 ( VERTICALS )
Task Team (Discipline): | BIM Department
Date: | 2024-10-19 09:56
Revision:
Document Reference: | 00103-CHEC-ZZZ-ZZZ-DOC-ZB-000001
[5 empty] | Naming convention | [8 empty] | Refer to Model Federation Strategy |  | Work stage: | Information delivery milestone
[21 empty] | Base line Dates |  | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
Document Number | Description | Exchange Formats | Sheet size (if applicable) | Scale | ProjeEP identifier | Originator | Zone/Volume | Level / location | Type | Discipline | Serial Number | Drawing Type | Information identification (automatic) | Discipline2 | Document Type | Responsible party | LOI | LOD | REV00 | Status (Latest / Superseded) | Submission BL Start | Submission BL Finish | Planned Submission Date | Submission Date / SITE | Contractor Status | Consultant Status | Reply Date | Review | REV01 | Status (Latest / Superseded) | Submission BL Start | Submission Date / SITE | Contractor Statues | Consultant Statues | Reply Date | Review | REV02 | Status (Latest / Superseded) | Submission Date / SITE | Contractor Statues | Consultant Statues | Reply Date | Review | REV03 | Status (Latest / Superseded) | Submission Date / SITE | Contractor Statues | Consultant Statues | Reply Date | Review | REV04 | Status (Latest / Superseded) | Submission Date / SITE | Contractor Statues | Consultant Statues | Reply Date | Review
DRAWING

## Naming References
Project Code |  | Originator |  | Zone |  | Levels |  | Document Type |  | Role/Discipline |  | Serial Number |  | Paper Size | Scale | Revision | Stage |  | Exchange Formats
Project Number | Project Name | Code | Originator Name | Code | Zones/Volumes | Code | Level/Floor Description | Code | Document Type | Code | Role | Code | Serial Number ( Refer to Serial Number Picklist) | Paper Size | Scale | Revision | Code | Stage | Exchange Formats
00000 | Group ROSHN | ACS | Arab Company for Laboratories and Soil (ACES) | XXX | No Volumes / Locations | XXX | No Level/Location Applicable | 3DM | 3D Model ( Engineering Models) | AE | Architectural Elements | 000000 | General | A0 | 1:1 | 00 | PV | Landoppurtunity and Site Pre Vision | PDF
00100 | Sedra-Common to all Phases | ACX | Aconex | ZZZ | All Volume / Locations | ZZZ | Multiple Levels/Locations | AGN | Agenda | AF | Architectural Finishes | 010000 | Plans | A1 | 1:2 | 01 | FV | Initial Feasability & Project Vision | DWG
00101 | Sedra Phase 1A | ADA | Assir Development Authority | ISA | Infrastructure Sedra ( Zone /Neighbourhood ) A | INF | Infrastructure utilities : used only when (IAG,IUG) codes are not applicable | ANC | Announcements | AI | Architectural Interiors | 020000 | Elevations | A2 | 1:5 | 02 | FS | Initial Feasability & Project Concept | RVT
00111 | Sedra Phase 1B | ADK | Adwaa Alkhalil Contracting | ISB | Infrastructure Sedra ( Zone /Neighbourhood) B | IAG | Above ground infrastructure utilities | AST | Assessment | AL | Architecture Fire life Safety | 030000 | Sections | A3 | 1:10 | 03 | CD | Concepet Design | NWC
00102 | Sedra Phase 2 | ADM | Advanced Media | ISC | Infrastructure Sedra ( Zone /Neighbourhood) C | IUG | Underground infrastructure utilities | ATS | Attendance Sheet | AW | Architecture Signage and Wayfinding | 040000 | Enlarged Plans/ Callouts放大图，详图索引 | A4 | 1:20 | 04 | SD | Schematic Design | NWD
00103 | Sedra Phase 3 | ADO | Avado learning | ISD | Infrastructure Sedra ( Zone /Neighbourhood) D | BFL | Building Foundations Level | CHK | Bank cheque | CC | Civil Infrastructure Chilled Water | 050000 | Enlarged Elevations放大立面图 | Custom | 1:50 | 05 | DD | Detailed Desing & Procurement | IFC
00104 | Sedra Phase 4 | ADP | Airport de Paris (ADPi) | ISE | Infrastructure Sedra ( Zone /Neighbourhood) E | BGF | Building Ground Floor | BOR | Bid Opening Record | CE | Earthworks | 060000 | Enlarged Sections放大剖面 | N/A | 1:100 | 06 | CH | Construction,Commissionin& Handover | XLS
00105 | Sedra Phase 5 | ADS | Adnan Abbas | ISF | Infrastructure Sedra ( Zone /Neighbourhood) F | B01 | Basement Level 01 | BOQ | Bill of Quantity | CF | Civil Firefighting Network | 070000 | Vertical Transportation楼梯图 | - | 1:200 | 07 | OP | 3 Years Operation&Maintenancie
00201 | Alkharj (Only One Phase) | AEM | Argus estate master | ISG | Infrastructure Sedra ( Zone /Neighbourhood) G | B02 | Basement Level 02 | PIM | Project Information Model | CG | Civil Geotechnical | 080000 | Details/Schematics详图 |  | 1:250 | 08
00301 | AlJanadriyah (Only One Phase) | AES | Aedas Architects FZ LLC | ISH | Infrastructure Sedra ( Zone /Neighbourhood) H | UGF | Upper Ground Floor | BND | Bonds ( e.g. Performance, Guarantee) | CI | Civil Infrastructure Irrigation Water | 090000 | Schedules清单 |  | 1:500 | 09
00401 | Riyadh Gateway B | AGU | Acciona Agua | ISI | Infrastructure Sedra ( Zone /Neighbourhood) I | LGF | Lower Ground Floor | BRO | Brochures | CM | Civil Infrastructure (MOI Fibre Optics Network) |  | 1.问智行数字后面的编码规则？如020000中2后面的编码规则 |  | 1:1000 | 10
00402 | Riyadh Gateway A | AGZ | Al Gihaz Co. | IMA | Infrastructure Makkah ( Zone /Neighbourhood ) A | P01 | Podium 01 | BDG | Budget | CP | Civil Infrastructure Potable Water |  |  |  | 1:1250
00403 | Riyadh Gateway C | AHC | Abahsain Consolidated Co. | IMB | Infrastructure Makkah ( Zone /Neighbourhood) B | P02 | Podium 02 | CPS | Capability Statement | CR | Utility Reservations / Combined Utility / Infra structure Ducts |  |  |  | 1:5000
00500 | Al Hofuf (Common to all phases) | AHP | Affordable Housing Program | IMC | Infrastructure Makkah ( Zone /Neighbourhood) C | P03 | Podium 03 | CRV | Cash Receipt Voucher | CS | Civil Storm Water |  |  |  | NTS
00501 | Al Hofuf Phase 1 | AHS | Abdul Aziz Hakbani Sons | IMD | Infrastructure Makkah ( Zone /Neighbourhood) D | L01 | level 01 | CPL | Change Proposal | CT | Civil Infrastructure Dry Utilities (Telecommunication)
00600 | Al Qatif (Common to all Phases) | AHT | Al Ahli Takaful | IME | Infrastructure Makkah ( Zone /Neighbourhood) E | L02 | level 02 | CKL | Checklist | CZ | Civil General
00601 | Al Qatif Phase 1 | AIC | Al Ayuni Investment and Contacting Co. | IMF | Infrastructure Makkah ( Zone /Neighbourhood) F | L03 | level 03 | CRF | Clarification | CW | Civil Infrastructure Waste Water
00701 | Dammam 1 (Only One Phase) | AIS | Aerial Imaging Saudi Arabia | IMG | Infrastructure Makkah ( Zone /Neighbourhood) G | L04 | level 04 | CHT | Chart | EA | Access Control/CCTV/Security /intercom
00801 | Dammam 2 (Only One Phase) | AJD | Al jedaie | IMH | Infrastructure Makkah ( Zone /Neighbourhood) H | L05 | level 05 | CRN | Credit Note | EB | Building Management system (BMS)
00900 | Al Arous (Common to all Phases) | AJM | Abdulali Al-Ajami Co. Ltd | IMI | Infrastructure Makkah ( Zone /Neighbourhood) I | L06 | level 06 | DSB | Dashboard | EC | Electrical Containments
00901 | Al Arous Phase 1 | AJS | A. J. Studio | IMZ | Infrastructure Makkah CEC | L07 | level 07 | DBN | Debit Note | EE | Renewable Energy
00902 | Al Arous Phase 2 | AMA | AMAM Co for Real Estate Appraisal | IQA | Infrastructure Al Qatif ( Zone /Neighbourhood ) A | LRF | Lower Roor | DRS | Design Review Sheet | EF | Fire Detection and Alarm
00903 | Upper Grand Canal | AME | Ahmed Almousa Eng'g Consultants | IQB | Infrastructure Al Qatif ( Zone /Neighbourhood) B | BRF | Building Roof | DPL | Disposal Approval & Authorization | EG | Grounding (Earthing) /Lightening Protection
00950 | Jeddah Renaissance | AMH | Abdulelah AlMohanna Engineering Consultants | IQC | Infrastructure Al Qatif ( Zone /Neighbourhood) C | URF | Upper Roof | DOC | Document | EL | Electrical Lighting
01000 | Jeddah South (Common to all Phases) | AMN | Arabian Security and Safety Services Ltd. Co. AMNCO | IQD | Infrastructure Al Qatif ( Zone /Neighbourhood) D | 1.site adaptation按照基础设施的标高 2.cluster按照基础和建筑层数 3.prototype按照基础和建筑层数 4.不涉及标高的按照“XXX”，系统图、详图等 5.多个标高的“ZZZ”，如剖面图、立面图等 |  | EML | Email | EN | Communications Networks (Data & Telephone)
01100 | Makkah (Common to all Phases) | ANQ | Ansaq Contracting Co. LTD | IQE | Infrastructure Al Qatif ( Zone /Neighbourhood) E |  |  | EST | Estimate | EP | Electrical Power
01101 | Makkah Phase 1 | APC | Arabian Projects Company | IQF | Infrastructure Al Qatif ( Zone /Neighbourhood) F |  |  | EVC | Evaluation Criteria | EU | Electrical Utilities
01200 | Abha (Common to all Phases) | ARA | Al Rashid Abetong | IQG | Infrastructure Al Qatif ( Zone /Neighbourhood) G |  |  | EOI | Expression of Interest | EV | Audio Visual/Clock/Public address
01301 | Turquoise (Only One Phase) | ARC | ARCADIS | IQH | Infrastructure Al Qatif ( Zone /Neighbourhood) H |  |  | FAX | Fax | HI | ITS ( Intelligent Traffic system)
01400 | KAIA | ARJ | Al rajhi Building and Construction | IQI | Infrastructure Al Qatif ( Zone /Neighbourhood) I |  |  | FCS | Field Change Sheet | HM | Mobility
|  | ARK | Arkitectonica Design and Project Management | IHA | Infrastructure Al Hofuf ( Zone /Neighbourhood ) A |  |  | FIR | Field Inspection Request | HP | Parking
|  | ARM | Saudi Aramco | IHB | Infrastructure Al Hofuf ( Zone /Neighbourhood) B |  |  | FST | Finance Statement | HR | Roads Network
|  | ASA | Asalt Arab | IHC | Infrastructure Al Hofuf ( Zone /Neighbourhood) C |  |  | FCH | Flow chart | HS | Highways& Roads Signage
|  | ASG | Advanced Shining Gulf Company | IHD | Infrastructure Al Hofuf ( Zone /Neighbourhood) D |  |  | GRV | Goods Receipt Voucher | HT | Public Transport
|  | ASM | Assir Municipality | IHE | Infrastructure Al Hofuf ( Zone /Neighbourhood) E |  |  | GUD | Guideline | HW | Highways
|  | ASP | AS and P - Albert Speer and Partner GmbH | IHF | Infrastructure Al Hofuf ( Zone /Neighbourhood) F |  |  | IMG | Image | LA | Landscape Architecture
|  | AST | ARAB SUPPLY and TRADING Co. (ASTRA) | IHG | Infrastructure Al Hofuf ( Zone /Neighbourhood) G |  |  | INP | Insurance Policy | MF | Fire Protection
|  | ASY | Assembly Studios Ltd | IHH | Infrastructure Al Hofuf ( Zone /Neighbourhood) H |  |  | IST | Instruction | MH | Mechanical HVAC
|  | ATA | Abdulmohsin Al theyab Architects and Partners | IHI | Infrastructure Al Hofuf ( Zone /Neighbourhood) I |  |  | INV | Invoice | MI | Mechanical Instrumentation
|  | ATH | Althunayyan Company for Professional Services | IDA | Infrastructure Dammam ( Zone /Neighbourhood ) A |  |  | LTR | Letter | MM | Medical Gas
|  | ATK | WS Atkins and Partners Overseas Engineering Consultants | IDB | Infrastructure Dammam ( Zone /Neighbourhood) B |  |  | LOA | Letter of Award | MN | Pneumatic
|  | ATR | Attar (FCM) | IDC | Infrastructure Dammam ( Zone /Neighbourhood) C |  |  | LOI | Letter of Intent | MO | Fuel Oil
|  | AUS | Artrabia UAV Services | IDD | Infrastructure Dammam ( Zone /Neighbourhood) D |  |  | LOC | Letter of Commitment | PU | Power Utilities
|  | AVA | Ava Arquitectura Tecnica Y Gestion SL | IDE | Infrastructure Dammam ( Zone /Neighbourhood) E |  |  | LTC | Limit of Credit | PD | Public Health Drainage
|  | AWJ | Awj International Contracting Company | IDF | Infrastructure Dammam ( Zone /Neighbourhood) F |  |  | LST | List | PP | Public Health Plumping
|  | AYN | Al Ayuni Investment and Contracting Company | IDG | Infrastructure Dammam ( Zone /Neighbourhood) G |  |  | MVR | Machinery & Vehicle Requirements | PW | Waste Management
|  | BAK | Bakery: Novels | IDH | Infrastructure Dammam ( Zone /Neighbourhood) H |  |  | MAN | Manual | QS | Quantity Surveying
|  | BAN | Bawan | IDI | Infrastructure Dammam ( Zone /Neighbourhood) I |  |  | MAP | MAP | SE | Structural systems
|  | BBT | Al Babtain Contracting Co. | IKA | Infrastructure Alkharj ( Zone /Neighbourhood ) A |  |  | MAT | Material Submittal | TM | Master Planning
|  | BCT | Boost Consulting and Trading | IKB | Infrastructure Alkharj ( Zone /Neighbourhood) B |  |  | MIR | Material Inspection Request | TU | Urban Design
|  | BDC | Build Consult | IKC | Infrastructure Alkharj ( Zone /Neighbourhood) C |  |  | MTX | Matrix | WM | Water Engineering( Marine Works)
|  | BDP | BDP MENA Consulting Engineers LLC | IKD | Infrastructure Alkharj ( Zone /Neighbourhood) D |  |  | MQS | Measurement Quality Sheet | YA | Survey / Mapping Aerial
|  | BEE | BE | IKE | Infrastructure Alkharj ( Zone /Neighbourhood) E |  |  | PIV | Media | YC | Survey / Mapping Computated Points
|  | BER | Berlitz | IKF | Infrastructure Alkharj ( Zone /Neighbourhood) F |  |  | MEM | Memorandum | YD | Survey / Mapping Digital
|  | BFL | Bofil Arquitectura SL | IKG | Infrastructure Alkharj ( Zone /Neighbourhood) G |  |  | MST | Method Statement | YF | Survey / Mapping Field
|  | BGK | Branch of Global Knowledge | IKH | Infrastructure Alkharj ( Zone /Neighbourhood) H |  |  | MIS | Miscellaneous Documents | YG | Survey Mapping - General
|  | BGU | Border Guard | IKI | Infrastructure Alkharj ( Zone /Neighbourhood) I |  |  | OCS | Observation & Comments | YI | GIS/Choropleth
|  | BHD | Buro Happold | VL1 | Villa Type 01 |  |  | PTC | Payment Certificate, Interim Pay. Cert. | YL | LIDAR
|  | BID | BID Computer Graphic Design Services LLC | VL2 | Villa Type 02 |  |  | PER | Permit | YN | National Grid
|  | BIL | Saudi Mobily Company | VL3 | Villa Type 03 |  |  | PLN | Plan | YS | Survey Control
|  | BJA | Bin Jarallah Group | VL4 | Villa Type 04 |  |  | POL | Policy | YT | Topographical
|  | BKY | Backyard | TH1 | Town House 01 |  |  | POA | Power of attorney | YU | Survey / Mapping Combined Utilities
|  | BLB | Bloomberg | TH2 | Town House 02 |  |  | PQL | Prequalification | ZB | BIM
|  | BMA | Bandar Almansoour Architects | TH3 | Town House 03 |  |  | PPT | Presentation | ZG | GIS
|  | BME | Boyden Middle East | DP1 | Duplex Type 02 |  |  | PRD | Procedure | ZS | Sustainability
|  | BMW | Broadway Malyan Limited | DP2 | Duplex Type 02 |  |  | PRF | Procurement Requisition | XX | Non Discipline
|  | BNY | Benoy LTD | DP3 | Duplex Type 03 |  |  | PIN | Program Invitation | ZZ | Multiple Disciplines
|  | BPW | Best Places To Work LTD | DP4 | Duplex Type 04 |  |  | PBF | Project Booking Form
|  | BRC | Bestar Creations Limited | QP1 | Quadruplex Type 01 |  |  | PRS | Proposal
|  | BRE | Building Roots | QP2 | Quadruplex Type 02 |  |  | POR | Purchase Order
|  | BSH | BRASH | C10 | Villa Type C10 |  |  | QUE | Query
|  | BTT | Bin Ghaith Tours | C11 | Villa Type C11 |  |  | QTN | Quotation
|  | BUR | Building Roots Est | C12 | Villa Type C12 |  |  | REC | Receipt confirmation of RFP
|  | BWN | Al Bawani | C13 | Villa Type C13 |  |  | REG | Registration / Logs
|  | BYG | Bouygues | C14 | Villa Type C14 |  |  | SCH | Schedule
|  | BYH | Saudi Real Estate Infrastructure (Binyah) | D07 | Villa Type D07 |  |  | SOW | Scope of Work
|  | BZA | Badar Z. Al-Abodi Est. | D09 | Villa Type D09 |  |  | SCU | S Curve
|  | CAA | Callison Architecture Inc - US | E01 | Villa Type E01 |  |  | SAU | Signatory Authorization
|  | CAB | Currie and Brown Saudi Arabia Limited | E03 | Villa Type E03 |  |  | SFC | Settlement & final Clearance
|  | CAC | CA - Collaborative Architects | W01 | Potable Water Tanks (Concrete/Steel) |  |  | SIN | Site Instruction
|  | CAJ | CCC - Archirodon JV | X01 | Disinfection System Building |  |  | SAL | Snag List
|  | CBD | Creative Blend | S01 | SEC building |  |  | SOI | Solicitation of Interest
|  | CBR | CBRE Advisory Services LLC | H01 | Guard House |  |  | SPE | Specification
|  | CCC | Consolidated Contractors Company | G01 | Generator room |  |  | STY | Study
|  | CCE | Contacting and Construction Enterprises | M01 | Flowmeter and Valve chambers |  |  | SCS | Supplier/Subcont. Comparison Sheet
|  | CDC | Communtiy Development Company | F01 | Fuel tank Base/Dyke |  |  | SRQ | Supply Request
|  | CHB | Chubb | P01 | Pump Room |  |  | SUR | Survey
|  | CHE | China Harbour Engineering Co Ltd. | JM1 | Jumaah Mosque |  |  | TMP | Template
|  | CHP | chapmanbdsp | LM1 | Local Mosque |  |  | TDR | Tender Documents
|  | CIP | Chartered Institute of Procurement and Supply (Dubai Branch) | NC1 | Neighbourhood Community Center |  |  | TRN | Training & Induction
|  | CIT | Communication and Information Technology Commission | PH1 | Public Healthcare / Primary Healthcare |  |  | TRS | Transmittal / Transmittal Letter
|  | CLD | CLYDE and CO. | CC1 | Public Clinic / Community Clinic |  |  | VID | Video
|  | CMC | Computer Cell | HP1 | Private Hospital |  |  | WOR | Work Order / Task Order / Work Inst.
|  | CMS | Create Media Services DMCC | CP1 | Private Clinic |  |  | WAR | Warranty
|  | CND | Command MENA | PO1 | Police Station |  |  | WSP | Work Shop
|  | CNT | Continental | CD1 | Civil Defence |  |  | PKG | Package
|  | CNW | Cushman and Wakefield | RC1 | Red Crescent |  |  | VOR | Variation Order
|  | COD | Barcode Company | SH1 | Shamel |  |  | CHO | Change Order
|  | COG | Hisham Nabil Alireza Trading Co. LTD C1 | KG1 | Kindergarten |  |  | NOA | Notification of Award
|  | COL | Collier | PS1 | Primary School |  |  | DWG | Drawing
|  | CPL | Capital Lights Co. For Electro Mechanics | ES1 | Elementary School / Intermediate School |  |  | 1.和智行询问，除了模型和cad形式还有其他的吗？另外模型和cad怎么划分？
|  | CRC | China Railway Construction | HS1 | High School / Secondary School
|  | CRK | CallisonRTKL-ME Ltd | NE1 | Nationwide City Experience Center
|  | CTC | China State Construction | CE1 | Small City Experience Center
|  | CVA | Collaborative Architects | HC1 | Handover Center
|  | DAA | Dr. Abdulgader Amir | CF1 | Community Facility Building
|  | DAE | Dar Engineering | DM1 | District Mall
|  | DAH | Dar Al Handasah | MF1 | Multifamily Building
|  | DAM | Sustainable Buildings | IS1 | Irrigation Water Station
|  | DBT | Dar Beta Information Technology | WS1 | Potable Water Station
|  | DCL | Delta Company Limited | BR1 | Bridge
|  | DCR | Draw and Color Contracting | PB1 | Pedestrian Bridge
|  | DDP | Dimension Data Pty. Ltd. | TU1 | Tunnel
|  | DEE | Dewan Architects and Engineers | OF1 | Offices
|  | DFC | Desert Fence Company (DEFCO) | FB1 | Food and Beverage
|  | DGD | Diriyah Gate ‍Development Authority | IC1 | Infrastructure Cluster 01 ( for Phase 1B)
|  | DGJ | DG Jones | IC2 | Infrastructure Cluster 02 ( for Phase 1B)
|  | DHI | Al Dhahry International | 1.site adaptation命名用基础设施的内容 2.prototype用别墅的命名，general的用ZZZ 3.需要向咨工澄清：cluster图纸用什么命名？（IC） D01:DP1*DP1; D02:DP2*DP2; D04:DP4*DP4; HX1:DP1*TH1*TH3*TH3*TH1*DP1; HX2:DP1*TH3*TH3*TH3*TH3*DP1; HX3:DP2*TH1*TH1*TH1*TH1*DP2; HX4:DP2*TH1*TH3*TH3*TH1*DP2; HX5:DP4*TH1*TH1*TH1*TH1*DP4; HX6:DP4*TH1*TH3*TH3*TH1*DP4; HX7:DP4*TH3*TH3*TH3*TH3*DP4; Q01:DP1*TH1*TH1*DP1; Q02:DP1*TH3*TH3*DP1; Q03:DP2*TH1*TH1*DP2; Q04:DP2*TH3*TH3*DP2; Q05:DP4*TH1*TH1*DP4; Q06:DP4*TH3*TH3*DP4;
|  | DIO | DIORAMA
|  | DLS | DynamicLearning-SixSeconds FZ - LLC
|  | DOM | Dar Al Omran for Consulting Engineering-SA
|  | DOR | Doroob
|  | DPL | DPL Studio
|  | DRC | Darren Comber
|  | DRY | Dar Al Riyadh Consultants
|  | DSA | DSA Architects International
|  | DTC | dnata Travel Company Limited
|  | DUP | Bupa Arabia
|  | DUX | Dubox by Amana
|  | EAE | Eight Art EST
|  | EAM | Eastern Municipality
|  | ECG | Engineering Consultants Group
|  | ECR | Water and Electricity Regulatory Authority
|  | EFE | EF Corporate Education Ltd
|  | EHC | Engineering House Company
|  | EJD | Ejadah Management
|  | EJT | Al Ejtiyaz Company For Contracting
|  | EJZ | Al Enjaz Trading and Contracting Company
|  | ELF | Events Investment Fund
|  | ELH | Earth Lighthouse Company
|  | ELT | Eliant Inc
|  | EMY | Ernst and Young ( EY)
|  | ENF | ENSTOA Foreign
|  | ENG | Engicon KSA
|  | ENL | ENSTOA local
|  | ENS | enso creative communication
|  | ERA | ERA-co
|  | ERD | EIRAD Trading and Contracting Co
|  | ERG | Ergo Home Group
|  | ERO | Ergo Oversears
|  | ESC | Enterprise Solutions Company
|  | ESM | Estate Master FZ LLC
|  | ESN | Esnad real estate valuation
|  | ESR | Esrar
|  | ESY | Energy Systems Company
|  | ESZ | Eslam Alzayat
|  | ETC | Ertyad Training company
|  | ETM | Developers Services Center
|  | ETP | ETOP Solution
|  | EVC | Event Communications Ltd
|  | EVV | Evolv Design
|  | EXT | eXtra
|  | EZO | EZ Order
|  | FAP | Foster and Partners
|  | FAR | Fairmont Riyadh
|  | FCM | Franklin Covey Middle East
|  | FEE | Al-Falak Electronic Equipment and Supplies Co.
|  | FNG | Faithful And Gould
|  | FNR | Al fanar
|  | FOS | Foster
|  | FRD | Al Faredah Hall
|  | FRZ | Fahd Alireza Engineering Consultants
|  | FVZ | FalconViZ
|  | GAC | General Authority of Civil Aviation
|  | GAM | General Authority for Military Industries
|  | GCA | General Court of Audit
|  | GDA | GOODAT
|  | GDC | General Directorate of Civil Defence
|  | GEA | General Entertainment Authorit
|  | GEM | Global Event Management
|  | GEU | Gensler Europe Ltd.
|  | GHZ | Al Gihaz
|  | GJC | Gregory and Jones Consultants
|  | GNK | Glint/Kibreet Production
|  | GSC | General Survey Commission
|  | GTA | General Tourism Authority
|  | GTK | Global Think Group Limited Company
|  | GUF | Gulf Engineering House
|  | HAK | Hosam Al Abdulkarim Architecture and Engineering Consultants
|  | HAM | Alhasa Municipality
|  | HBS | Harvard Business School
|  | HCO | Al Hamdan Consulting Office
|  | HCP | HHCP
|  | HDR | HDR Middle East LLC
|  | HER | HERE S.R.L Advertising Services
|  | HGS | Hanmi Global Saudi
|  | HIG | Heights
|  | HIL | Hill
|  | HKB | Al Hakbani Group - Nutech IT Solutions
|  | HKS | HKS Co.
|  | HNO | Hanover Communications Middle East FZ-LLC
|  | HOC | House of Consulting Office
|  | HOK | HOK International Ltd Registered
|  | HOP | Hopkins Architect Dubai Limited
|  | HRT | HireRight
|  | HYG | Hygiene
|  | HYU | Branch Of Hyundai Engineering and Construction Co. Ltd.
|  | IDC | Idea Creations
|  | ILY | ILYA Medical Company
|  | INF | Informa Middle East
|  | INN | Innovative Options
|  | INS | Informa Saudi Arabia Ltd
|  | IOC | Bin Omairah Co.
|  | IOS | IPSOS
|  | ISA | Ministry of Investment
|  | ITL | Integrated Telecom Company
|  | JAL | JALNT
|  | JAR | Al Jomaih Auto Rental Company
|  | JAS | Jasarra
|  | JCB | CH2M Saudi Ltd Jacobs Engineering Group Inc.
|  | JDM | Jeddah Municipality
|  | JET | Jether
|  | JFP | Jowan Future Printing and Design
|  | JKP | Jack Pringle
|  | JLL | Jones Lang LaSalle JLL
|  | JMC | Jane McAuliffe
|  | JOM | ALJOMAIH AUTOMOTIVE COMPANY LIMITED
|  | JOU | Joule-Group
|  | JPM | Jeddah Project Management Office
|  | JRR | Jarir bookstore
|  | JTH | Jather Production
|  | JTP | JT+PARTNERS
|  | KAA | Khatib and Alami Arabia
|  | KAS | Al khwarizmi Actuarial Services Company (Akhtar and Hasan (Pvt) Ltd Actuaries)
|  | KCH | K Tech Company
|  | KEO | KEO International Consultants
|  | KFD | KAFD
|  | KFM | Knight Frank Middle East Limited – Saudi Arabia
|  | KFS | King Faisal Specialist Hospital & Research Centre
|  | KHA | Alkhwarizmi Actuarial Services Company
|  | KHE | Khalid Al Hamdan Engineering Consulting Office
|  | KHM | Al Kharj Municipality
|  | KHR | Abdul Kader Suleiman El Khereiji and Partner
|  | KHS | Khoshaim and Associates
|  | KHT | Khabeer Al Tathmeen Al Aqaria
|  | KHZ | Mohammad Abdulrahman khazim Est K-TECH
|  | KIL | Killa Architectural Design
|  | KLC | Al Kamlin Trading and Contracting Co
|  | KPG | KPMG Al Fozan and Partners
|  | KRN | A. T. Kearney
|  | KTC | Kettle Collective LTD
|  | KTT | Mohamed Reda Fouad Kattan
|  | KUZ | Al Kuzama Trading Company
|  | KZC | Kristina Zanic Consultants
|  | LAD | Legal Advisors
|  | LBR | Louis Berger
|  | LDA | LD+A Ateliers
|  | LDR | Landor Associates Europe
|  | LKN | LinkedIn Ireland Unlimited Company
|  | LME | Last Minute Event Management
|  | LMH | Limah Design
|  | LNS | Landsterling
|  | LON | Leoron
|  | LST | Linesight
|  | LTS | Larsen and Toubro Saudi Arabia LLC
|  | LTT | ITL Leisure tourism and travel co.
|  | LUS | Lunas
|  | LWZ | Lawazem For Trading and Marking
|  | MAC | Mace Arabia Engineering Consultancy
|  | MAF | MFAZ for Land Appraisal
|  | MAM | Mohammed AlAmmar
|  | MAR | MARINA INC.PRINTERS
|  | MAT | Masaya Al Zuhoor Trading Est.
|  | MBN | Al mabani General Contrators
|  | MBS | Modern Binding System
|  | MCI | Ministry of Commerce and Investment
|  | MCM | My Cam
|  | MCP | Michael Page
|  | MCT | Ministry of communication and information Technoligy
|  | MDA | Al Madinah Region Development Authority
|  | MDH | The Law Firm of Mohammed AlDhabaan
|  | MDM | Madinah Municipality
|  | MDN | Mohammed AlDabaan
|  | MDR | Al madar Advertising and Public Relations Agency
|  | MEA | 360MEA For Information Technology (360VUZ)
|  | MEC | Money Experts Institute for Training
|  | MED | Meed
|  | MEN | Middle East News
|  | MER | Mercer
|  | MET | Riyadh Metro
|  | MFF | Momaizah Metal Fabrication Factory LLC.
|  | MFT | Madaf Trading and Contracting Co. Ltd
|  | MGI | Morganti Project Management - Riyadh, KSA
|  | MHC | Mofarreh Al-Harbi and Partners Co. Ltd - Harbico
|  | MIA | Miahona
|  | MIC | Military Industries Corporation
|  | MIL | Millward Brown Saudi Arabia LLC
|  | MIM | Minister of Industry and Mineral Resources
|  | MIR | Mira
|  | MIT | Mohammed Alzahid IT Est.
|  | MJZ | Moqawel Jazerat Al Arab Contracting Company
|  | MKM | Makkah Municipality
|  | MKT | Maktabi
|  | MKY | McKinsey
|  | MMC | Microtics Management Company
|  | MMK | Mumtalakat- Saudi Korean Company
|  | MML | Mott Macdonald
|  | MMR | Ministry of Municipal and Rural Affairs and Housing
|  | MMS | Mohamad M. Shurrab Trading Establishment (Profiles Arabian)
|  | MNA | Meinhardt arabia
|  | MNF | Manafe Economic Real Estate
|  | MNG | Ministry of National Guard
|  | MOA | Ministry of Islamic Affairs Dawah and Guidance
|  | MOC | Ministry of culture
|  | MOD | Ministry of Defense
|  | MOE | Ministry of Education
|  | MOF | Ministry of Finance
|  | MOH | Ministry of Health
|  | MOI | Ministry of Interior
|  | MOJ | Ministry of Justice
|  | MON | Ministry of Energy
|  | MOO | Ministry of Tourism
|  | MOS | Ministry of Sports
|  | MOT | Ministry of Transport
|  | MRD | Makkah Region Development Authority
|  | MRT | MIRTCO Company
|  | MRY | MARYNOON
|  | MSC | Masco Group
|  | MSL | Metito Saudi Ltd.
|  | MSP | Martha Schwartz Partners
|  | MTC | Meirc Training and consulting
|  | MTN | Maham Altanmia Trading Co
|  | MVE | MVE and Partners Inc.
|  | MWA | Ministry of Environment, Water and Agriculture
|  | MWN | National Center for Waste Management
|  | MZD | Mohammed Al Zahid
|  | NAJ | Najiz
|  | NCC | National Contracting Company
|  | NCE | National Center for Environmental Compliance
|  | NCO | NACO HaskoningDHV Saudia Engineering Consultancy
|  | NCP | National Center for Privatization and PPP
|  | NGA | Naga Architects
|  | NGD | National Grid SA
|  | NGE | Naizak Global Engineering Systems
|  | NGP | Nesma Group
|  | NHC | National Housing Company
|  | NHL | Nahil Computers
|  | NIW | Nesma International Water and Energy Technology Ltd. Co.
|  | NKC | alnesma althakia commercial company
|  | NOR | Nournet Communication Co.
|  | NRS | National Real Estate Registration Services Company
|  | NSA | Nahed saleh aboud alamoudi
|  | NSE | Nesma Security Services Company
|  | NSI | NSI Talent
|  | NSM | Nesma and Partners Contracting Co.
|  | NUT | NuTech IT Solutions
|  | NWC | National Water Company
|  | NWJ | NEW Job
|  | OAO | OAOA Ltd
|  | OBI | Observatory International
|  | OJM | Al Ojaimi
|  | OMA | Omrania and Associates
|  | OMC | Al Omair Contracting Company
|  | OMN | Omnium International Company LLC
|  | OMR | Omran Architevts and Engineering Consultant
|  | OMX | Omnix International
|  | ONE | One Touch Medical Company
|  | ONS | Onsor Mosha Advertising Company
|  | ONV | One Vision For Trading EST
|  | ORC | Oracle Systems Limited
|  | ORS | Orascom Construction SAE
|  | OST | Al Ostool Al Aali
|  | OTC | Al Omaier Trading and Contracting Co.
|  | OWY | Oliver Wyman
|  | PAT | Pattis
|  | PEC | platin event co
|  | PIF | Public Investment Fund
|  | PIH | PixelHunters
|  | PKE | Perkins Eastman
|  | PLP | PLP Architecture
|  | PME | Presidency of Meteorology and Environment
|  | PMP | p2m Berlin GmbH
|  | PNH | Pennel Hart
|  | POP | Populous
|  | POS | POPLARS
|  | PPV | PPV worldwide
|  | PRG | Precise Gifts Company LTD.
|  | PRS | Professional Realtors Company LLC - Colliers
|  | PRT | Protiviti Saudi Member Firm for Management Consultancy
|  | PSC | POSCO EandC Saudi Arabia
|  | PSN | Saudi Arabian Parsons Limited.
|  | PSS | Presidency of State Security
|  | PUA | Public Utilities Authority
|  | PUM | Pure Minds
|  | PWC | Price water house Coopers
|  | QDT | Quaid Telecom Company
|  | QER | Qemmet Alrawasi Contracting Co.
|  | QOL | Quality of life Program
|  | QTA | Qdesign Tasmeem AL Khamis
|  | QTM | Al Qatif Municipality
|  | QTR | Al Qotr Surveying Office
|  | RAC | Riyadh Airport Company
|  | RAM | RAM Contracting Ltd.
|  | RCH | Richmondcs KSA
|  | RCM | Royal Commission for Makkah City and Holy Sites
|  | RDP | Redpath Partners HR Consultancy
|  | RDT | Radees Trading Est.
|  | REM | Remal Assawahel Contracting and Maintenance Co. LTD
|  | RET | Retailo
|  | RFC | Royal Commission for Riyadh City
|  | RGA | Real State General Authority
|  | RGC | Rezaik Abdallah Al-Gedrawy and Co.
|  | RGP | Riyadh Green Program
|  | RIA | Riyadh Municipality
|  | RIF | Riyadh Front
|  | RIT | The Ritz-Carlton
|  | RJY | Royal Commission for Jubail and Yanbu
|  | RMJ | RMJM
|  | RNZ | Rabiah- Nassar and Zamil Concrete
|  | ROG | PROGER
|  | RPI | RP International Labor Supply
|  | RPN | Riyadh Primary Notarial Office
|  | RPR | Repstor
|  | RRE | Roshn Real Estate ( Appointing Party
|  | RRS | Rabigh Roads Security
|  | RSB | Rasem Badran
|  | RSD | Al Rashid For Trading And Contracting Co.
|  | RSI | Red Sea International
|  | RSM | RSCM
|  | RTC | Al Rashid Trading and Contracting Company LTD
|  | RTD | Rabigh traffic department
|  | RTL | RTKL ME Ltd
|  | RVC | Revonic Web Design LLC
|  | RWM | Rawdah Municipality
|  | RZE | Raz Exhibits
|  | SAH | Sahat Alalwan
|  | SAL | Salam
|  | SAM | Saudi Arabian Military Industries
|  | SAN | Saudi Air Navigation Services
|  | SAR | Saudi Railways Company
|  | SAT | Saudi Arabian Trading and Construction Company SATCO
|  | SBG | Saudi Binladin Group
|  | SBM | Saudi Business Machines Ltd.
|  | SBS | Saudi Bashayer Construction Co
|  | SCE | Saudi Consolidated Engineering Khatib and Alami
|  | SCS | Saudi Consulting Services
|  | SCT | Scott Brownrigg Limited
|  | SDA | Sharqia Development Authority
|  | SDC | Saudi Diyar Consultants
|  | SEC | Saudi Electricity Company
|  | SEF | El-Seif
|  | SEP | Saifee Events Pvt Ltd
|  | SET | Stars of Excellence IT EST TALLY
|  | SEU | Institute of research and studies (SEU)
|  | SFB | Strategy and Formerly Booz
|  | SFO | Salfo and Associates Saudi Arabia
|  | SFU | Shaping the Future
|  | SGL | Spearhead Gulf LLC
|  | SGM | SIGMA IT Saudi For Telecommunications and Information Technology Co
|  | SGR | Strategic Gears Management Consultancy
|  | SGS | Saudi Geological Survey
|  | SHF | Al Sharif Group and KEC
|  | SHG | Al Sharif Group for Contracting and Dev. Trad.
|  | SHJ | Shibh Al Jazira
|  | SHL | Al Shalawi International Co.
|  | SHN | Al-Shahin Travel and Tourism,
|  | SHS | SHL Saudi Arabia Limited
|  | SHY | Sinohydro Corporation Ltd
|  | SIC | Saudi Icon Company
|  | SIO | Saudi Irrigation Organization
|  | SKO | Skidmore Owings and Merrill LLP
|  | SLA | Sela
|  | SLC | The Saudi Pro League Championship
|  | SLG | Siegel+Gale Limited
|  | SLN | Salini Saudi Arabia
|  | SLT | Advanced Energy for Sound and Light Technologies ltd
|  | SMC | Saudi Media Company
|  | SMH | Smart Hiring
|  | SMN | Siemens
|  | SMS | Samsung Engineering
|  | SMZ | security matterz
|  | SNC | SNC - Lavalin
|  | SNG | Saudi Arabian National Guard
|  | SNJ | Al Sahban and AlAjaji
|  | SOM | SOMAC Contracting Company
|  | SOR | Soor
|  | SOT | Saota Architects
|  | SOX | Solex Plus
|  | SPC | Saudi Pan Kingdom, SAPAC
|  | SPG | State Properties General Authority
|  | SPJ | Shapoorji Pallonji Mideast LLC
|  | SPS | Saudi Paramount Computer Systems
|  | SPT | Saudi Post
|  | SRE | Saudi Real Estate Infrastucture Company
|  | SRY | Saraya Al Andalus For Contracting
|  | SSA | Strategy and Saudi Arabia
|  | SSD | Salman AlSudairy
|  | SSE | Saudi Services For Electro Mechanic Works co. (SSEM)
|  | SSH | SSH-Sadoon Al Essa and Partner Consulting Engineers
|  | SSS | System Security Solutions Company
|  | STA | Statista
|  | STC | STC Solution
|  | STF | Shaping the future consultancy
|  | STM | Al Sallom AlToaimi
|  | STS | Studio Schiattarella Associati
|  | STT | Stream It for Informantion Technology
|  | SWJ | Al Sulaim AlAwaji
|  | SYN | Synsols
|  | SYR | Symmetry Research Consultants
|  | TAK | Takleem
|  | TAM | Tamimi Pre Engineered Buildings Co PEB
|  | TAQ | Taqnia ETS
|  | TAS | TASECO
|  | TBC | Tatweer Buildings Company
|  | TCC | TheThird Chemical Engineering Construction
|  | TCO | Saudi Public Transport Company
|  | TDM | Tact Digital Marketing
|  | TDS | Ten Design FZ-LLC
|  | TEC | Technical Accountancy(MORGANINTL)
|  | TFZ | THINKUBATOR FZ-LLC (360xworld)
|  | TGA | Transport General Authority
|  | THU | Al Thunyan Group
|  | TJC | Tareg Al-Jaafari Cont. Est
|  | TND | Trading and Development Partnership
|  | TPC | Touchpoints Consulting and Communications LTD
|  | TQS | Turquoise
|  | TRC | Theeb Rent A Car
|  | TRP | Thomson Reuters (Professional) UK Limited
|  | TST | Tamimi and Saihati Transport co .LTD
|  | TUM | Tabuk Municipality
|  | TWA | Tawuniya
|  | UDA | Udacity Inc.
|  | UKM | Unikomm
|  | URB | Urbis
|  | UTG | United Tri Generation (UTG)
|  | VEO | Veolia
|  | VET | Value Experts
|  | VIO | Visulisation One
|  | VIS | Vision Studio
|  | VLL | Visualisation One (London) Limited
|  | VOD | Vero Digital
|  | VST | ValuStrat
|  | WAF | Off-Plan Sales or Rent
|  | WEB | Webuild
|  | WHT | Washnah Trading and Contracting
|  | WLF | WOLFF Online
|  | WLY | Worley
|  | WOB | Woods Bagot PTY Dubai Branch
|  | WOP | Wood PLC
|  | WPO | West professional organization
|  | WRD | Ward Restaurant
|  | WSP | WSP Middle East
|  | WTG | WATG Singapore Inc
|  | WTH | Wealthvox
|  | WTS | White Space
|  | WWS | WinnersWings
|  | YAM | Al Yamama Company
|  | YEN | Yenigun
|  | YGG | You gota gift
|  | ZAZ | Zuheir Ahmad Al Zahran and Company
|  | ZFH | Zoofitech Company LTD
|  | ZFP | Zuhair Fayes Partnership Consultants
|  | ZHB | Zaid Al Hussain and Brothers Group
|  | ZHD | Al zahid
|  | ZIN | Zain